## Sheet1
MCI Game Development
| Task Name | Duration | Start | Finish | Predecessors | Resource Names
| MCI Game Development | 59 days | Wed 3/4/20 | Mon 5/25/20
1 | Develop SDL Teaching Program | 8 days | Wed 3/4/20 | Fri 3/13/20
2 | Learn SDL | 5 days | Wed 3/4/20 | Tue 3/10/20 |  | SDL group
3 | Create teaching documents | 2 days | Wed 3/11/20 | Thu 3/12/20 | 2 | SDL group
4 | Send out precourse documents | 1 day | Fri 3/13/20 | Fri 3/13/20 | 3 | SDL group
5 | Teach SDL | 0 days | Fri 3/13/20 | Fri 3/13/20 | 4 | SDL group,All
6 | Standards | 27 days | Wed 3/4/20 | Thu 4/9/20
7 | Develop Standards | 3 days | Wed 3/4/20 | Fri 3/6/20 |  | Standards
8 | Create preliminary UML | 2 days | Wed 3/25/20 | Thu 3/26/20 | 17 | Standards,Graphics,Logic
9 | Maintain UML | 10 days | Fri 3/27/20 | Thu 4/9/20 | 8 | Standards
10 | Source Control | 5 days | Wed 3/4/20 | Tue 3/10/20
11 | Research file share platforms | 3 days | Wed 3/4/20 | Fri 3/6/20 |  | Source Control
12 | Prepare documentation | 1 day | Mon 3/9/20 | Mon 3/9/20 | 11 | Source Control
13 | Present to class | 1 day | Tue 3/10/20 | Tue 3/10/20 | 12 | Source Control
14 | Game Concept Development | 27 days | Wed 3/4/20 | Thu 4/9/20
15 | Initial Game Concept Vote | 0 days | Wed 3/4/20 | Wed 3/4/20 |  | All
16 | Concept development | 7 days | Wed 3/4/20 | Thu 3/12/20 | 15 | Game group
17 | Customer concept preview | 0 days | Wed 3/25/20 | Wed 3/25/20 | 16
18 | Develop graphics prototype | 10 days | Fri 3/27/20 | Thu 4/9/20 | 8 | Graphics group
19 | Develop logic prototype | 10 days | Fri 3/27/20 | Thu 4/9/20 | 8 | Logic group
20 | Testing | 3 days | Fri 4/10/20 | Tue 4/14/20
21 | Test graphics | 3 days | Fri 4/10/20 | Tue 4/14/20 | 18 | Test group
22 | Test logic | 3 days | Fri 4/10/20 | Tue 4/14/20 | 19 | Test group
23 | Integration | 18 days | Wed 4/15/20 | Fri 5/8/20
24 | Combine graphics and logic | 14 days | Wed 4/15/20 | Mon 5/4/20 | 21,22 | Integration group
25 | Test integration | 4 days | Tue 5/5/20 | Fri 5/8/20 | 24 | Integration group
26 | Integration testing complete | 0 days | Fri 5/8/20 | Fri 5/8/20 | 25
27 | Documentation | 15 days | Tue 5/5/20 | Mon 5/25/20
28 | User help/manual | 3 wks | Tue 5/5/20 | Mon 5/25/20 | 24 | Communications
29 | Project Presentation | 4 days | Tue 5/5/20 | Fri 5/8/20
30 | Create presentation | 4 days | Tue 5/5/20 | Fri 5/8/20 | 24 | Communications
31 | Present to MCI | 0 days | Fri 5/8/20 | Fri 5/8/20 | 26,30 | Communications
32 | Deployment | 22 days | Fri 4/10/20 | Mon 5/11/20
33 | Research deployment methods | 5 days | Fri 4/10/20 | Thu 4/16/20 | 19 | Deployment Team
34 | Determine final deployment strategy | 5 days | Fri 4/17/20 | Thu 4/23/20 | 33 | Deployment Team
35 | Develop deployment methodology | 1 day | Fri 4/24/20 | Fri 4/24/20 | 34 | Deployment Team
36 | Secure deployment resources | 1 day | Mon 4/27/20 | Mon 4/27/20 | 35 | Deployment Team
37 | Deploy software | 1 day | Mon 5/11/20 | Mon 5/11/20 | 36,26 | Deployment Team
38 | Deployment complete | 0 days | Mon 5/11/20 | Mon 5/11/20 | 37